## Timesheet
Student Name: | Daniel Marzari
Date | 2019-05-06 |  | Plan vs. Actual Analysis
Project Name | Alumni Connect
| Project Phase | Plan | Actual | Difference
| Planning | 5.5 | 5 | 0.5
| Design | 14 | 11 | 3
| Coding | 57 | 65 | -8
| SIT | 19 | 29.5 | -10.5
| UAT | 6 | 2 | 4
| Training / Documentation | 27 | 13 | 14
| Deployment | 1.5 | 13.5 | -12
| Hypercare | 7 | 17.5 | -10.5
| Baseline | 137 | 156.5 | -19.5
| 15% Contingency | 157.55 | 156.5 | 1.05
Period 1 - 1st through 15th
Period 2 - 16th through month-end