## Slide 1: Alumni Connect Project Roadmap
Daniel Marzari

## Slide 2: Goals of Alumni Connect
Alumni Connect was created to cultivate university relations with alumni by providing various services to them and encouraging their continued involvement with the university, and investment in current students.
Objectives:
Alumni Accounts (register, update/recover password)
Alumni Profiles (add, browse, connect, contact, delete/deactivate, update)
Administrator Reporting (queries with various criteria)
Self-Service portal (view transcript, diploma, and register for audits)
University Events (add, view, add to calendar/get notifications)
Forum Post (general communication with alumni and staff, job/internship opportunities, chapel/event speaker sign-up, mentorship/sponsorship inquiries)
Integration with Cairn app or separate mobile interface

## Slide 3: Current Features
Within the first 6 months of development, the following features have been successfully added. This system should be considered a beta test and will not be an official release until June of 2021.
Alumni Accounts (imported, no registration or password recovery)
Alumni Profiles (add, browse, contact, update)
Administrator Reporting (queries with various criteria)
Self-Service portal (view transcript, get new diploma)
University Events (add, view)
Forum Post (general communication)

## Slide 4: Completed Development
Plan
Launch
Jan
Feb
Mar
Apr
May
2020
Agile Project Management
Feature List, Site Map, UML Diagram
Project Quote
Test
Monitoring
UAT
SIT
Database Integration
Heroku Integration
Develop
Development Phase 1
System Go-Live
Test Deployment
Public Release
May 1, 2020
Project Kickoff
Jan 22
Project Review
Feb 12
Project Approval
Feb 19
Beta Release
Apr 22
Test Deployment
Apr 1
Final Release
May 1
Project Model
Testing Plan
Implementation Plan
Training Plan
Remediation
Hypercare
(Beta) Heroku Deployment
April 22, 2020
User Training Presentation
April 22, 2020
Database Launch
March 8, 2020

## Slide 5: Short-Term Release
Within the next 6 months, there will be two small releases (3 month cycles) that will address essential features that were not able to be completed in the initial deployment. These release features are high value and low risk and were only omitted because of time constraints.
Release Focus:
Alumni Accounts (register, update/recover password, two-factor authentication, single sign on via Gmail or Facebook)
University Events (auto-pull from official event planning at the university, add to Apple/Google calendar, and get email or text notifications, mark attending)

## Slide 6: Long-term Release I
Beginning in December of 2020, there will be a release that will take 6 moths. The focus of this update is to add the ability for users to connect with other users. New features will be added to enable Alumni Connect to function similar to social media applications.
Release Focus:
User Connecting
  Alumni, Students, Staff, and Organizations (internal) able to connect with each other
  Share PIIs only when connected
  Share updates, posts, activity, etc.
  Internal Forum to post job/internship opportunities, and inquire about opportunities at the university

## Slide 7: Long-Term Release II
Beginning in June of 2021 there will be another release which will take 9 moths. The focus of this update is to either merge Alumni Connect with the current Cairn University phone app or to make a standalone app expressly for Alumni Connect all while sustaining the online version. At the end of this release, the only foreseeable changes will be minor bug fixes or feature additions and the system can be officially advertised to alumni.
Release Focus:
Migrate to Mobile
  Mobile friendly UI (redesign likely)
  Integration into established university app
  Connection to other mobile apps for ease of use (messages, email, calendar, social media, notifications, etc.)

## Slide 8
Future Developments
Short Term Release I
Long Term Release II
Jun 2020
Long Term Release I
Short Term Release II
AC 1.1 Kickoff
Jun 10
Project Review
Sep 1
Beta Mobile Release
Sep 15
Beta Test
Mar 20
Final Release
Oct 15
Apr 10, 2021
Sep 2020
Dec 2020
Mar 2021
Jun 2021
Sep 2021
AC 1.2 Kickoff
Sep 10
AC 2.0 Kickoff
Dec 10
AC 3.0 Kickoff
Jun 1
Dec 2021
Development & Hypercare
Planning
Testing
Deployment
Aug 20, 2020
Development & Hypercare
Planning
Testing
Deployment
Nov 20, 2020
Development & Remediation
Planning
SIT
Hypercare
UAT
Project Review
Dec 1
Beta
Deployment
Oct 15, 2021
Development & Remediation
Planning
SIT
Hypercare
UAT
Beta
Deployment
Monitoring
Public Release & Ads
Dec 15

## Slide 9: Completion of Alumni Connect
By the spring semester of 2022, Alumni Connect will fully satisfy all proposed objectives known to date. The university will need to continue advertising and encouraging the use of the system as new students graduate. Again, it is the hope of the university to engage Alumni to cultivate university relations encouraging them to join and support the university as it prepares future generations of biblically minded, well-educated, and professionally competent men and women of character.